## Report
Phishing Detection Tool with Real-Time Threat Intelligence
Earned Value Analysis Report
| Prepared By: | Branden Si
| Date: | 2024-11-29
[42]
| For Period: | October 25, 2024 - November 29, 2024
Summary: Summary: Budget at Completion (BAC) for the project is $1285 that is, the amount which is being planned for all the tasks collectively. Earned Value (EV) which measures the amount of work accomplished till date is $ 1210. The Actual Cost (AC), or the amount of money already spent is $1,215, Thus the Cost Variance (CV) is - $755. This indicates that the cost of the project is exceeds the cost available for the same thus meaning that the cost of the project is high. Schedule performance index is equal to 0.36 which is actually less than 1 and it forecast that project is behind schedule. This means the project is currently not expending funds as per the planned efficiency and the cost performance index is 0.38. With regards to the current performance EAC is equal to 3394$. This means that there is possibility of cost exceeding the baseline with Variance at completion as;- $2,109.
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1.1 | Project Plan | 200 | 20 | 30 | 40 | 50 | 60
1.2 | Risk Management Plan | 150 | 10 | 20 | 40 | 40 | 40
1.3 | Project Management Plan | 300 | 30 | 40 | 60 | 70 | 100
1.4 | Application with GUI | 260 | 25 | 35 | 60 | 70 | 70
1.5 | Data Analysis | 155 | 15 | 20 | 30 | 40 | 50
1.6 | GitHub Repository | 220 | 20 | 30 | 50 | 70 | 50
| Total Budgeted Cost | 1285 | 120 | 175 | 280 | 340 | 370
|  | Cumulative Planned Value (PV) | 120 | 295 | 575 | 915 | 1285
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 85 | 220 | 465 | 820 | 1215
|  | Cumulative Earned Value (EV) | 100 | 160 | 280 | 410 | 460
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 15 | -60 | -185 | -410 | -755
|  | Schedule Variance (SV = EV - PV) | -20 | -135 | -295 | -505 | -825
|  | Cost Performance Index (CPI = EV/AC) | 1.1765 | 0.72727 | 0.60215 | 0.5 | 0.3786
|  | Schedule Performance Index (SPI = EV/PV) | 0.83333 | 0.54237 | 0.48696 | 0.44809 | 0.35798
|  | Estimated Cost at Completion (EAC) | 1092.25 | 1766.875 | 2134.0179 | 2570 | 3394.0761
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1.1 | Project Plan | 200 | 20 | 30 | 40 | 50 | 60
1.1 | Risk Management Plan | 195 | 15 | 25 | 35 | 55 | 65
1.2 | Project Management Plan | 145 | 5 | 15 | 30 | 45 | 50
1.3 | Application with GUI | 280 | 20 | 30 | 55 | 65 | 110
1.4 | Data Analysis | 240 | 20 | 25 | 55 | 75 | 65
1.5 | GitHub Repository | 150 | 10 | 15 | 25 | 45 | 55
1.6 | Task 6 | 200 | 10 | 20 | 40 | 75 | 55
| Cumulative EV | 1410 | 100 | 160 | 280 | 410 | 460
Actual Cost (AC) of Work Performed
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1.1 | Project Plan | 200 | 20 | 30 | 40 | 50 | 60
1.2 | Risk Management Plan | 145 | 5 | 15 | 30 | 45 | 50
1.3 | Project Management Plan | 280 | 20 | 30 | 55 | 65 | 110
1.4 | Application with GUI | 240 | 20 | 25 | 55 | 75 | 65
1.5 | Data Analysis | 150 | 10 | 15 | 25 | 45 | 55
1.6 | GitHub Repository | 200 | 10 | 20 | 40 | 75 | 55
| Total Actual Cost | 1215 | 85 | 135 | 245 | 355 | 395
|  | Cumulative Actual Cost (AC) | 85 | 220 | 465 | 820 | 1215
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)
Note on A44: Work Breakdown Structure (WBS)
Note on C44: Total Budgeted Cost (TBC)
Note on A55: Work Breakdown Structure (WBS)
Note on C55: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP). | [14 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [14 empty] | © 2012 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Project Plan | 200
1.2 | Risk Management Plan | 150
1.3 | Project Management Plan | 300
1.4 | Application with GUI | 260
1.5 | Data Analysis | 155
1.6 | GitHub Repository | 220
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
Insert new rows above this one
|  | Cumulative EV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Project Plan
1.2 | Risk Management Plan
1.3 | Project Management Plan
1.4 | Application with GUI
1.5 | Data Analysis
1.6 | GitHub Repository
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
Insert new rows above this one
|  | Total Actual Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0